## Budget
Project Budget Worksheet (USD)
For grants above USD 100k. Approved column locks on award. Actuals and commitments posted weekly by FM. Variance flag at 10%.
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Project | UNHCR-PPA-2026 Multipurpose cash, Ninewa
Donor | UNHCR
Start | 2026-01-01 | End | 2026-12-31
Months elapsed | 8 | Total months | 12
Budget flexibility between lines without donor approval | 10%
Line code | Category | Description | Unit | Unit cost | Qty | Frequency | Donor share % | Approved total | Donor approved | Cost share | Actual to date | Committed | Total spent + committed | Remaining | % burned | Expected % (time) | Variance vs time | Flag | Forecast to completion | Note
1.1 | Personnel | Project Manager (60%) | month | 3000 | 1 | 12 | 100% |  |  |  | 21600 | 0
1.2 | Personnel | M&E Officer (60%) | month | 1800 | 1 | 12 | 100% |  |  |  | 12960 | 0
1.3 | Personnel | Field Officers x4 | month | 1100 | 4 | 12 | 100% |  |  |  | 35200 | 0
2.1 | Programme | Multipurpose cash transfers | household | 400 | 1200 | 1 | 100% |  |  |  | 320000 | 30000
2.2 | Programme | Post-distribution monitoring (enumerators) | day | 25 | 240 | 1 | 100% |  |  |  | 4000 | 0
2.3 | Programme | Cash delivery service fees | transfer | 3 | 1200 | 1 | 100% |  |  |  | 2400 | 0
3.1 | Operations | Office rent Mosul (shared 40%) | month | 800 | 1 | 12 | 100% |  |  |  | 3840 | 0
3.2 | Operations | Vehicle hire and fuel | month | 900 | 1 | 12 | 100% |  |  |  | 7200 | 1500
3.3 | Operations | Translation services | 1000 words | 40 | 60 | 1 | 100% |  |  |  | 1200 | 0
4.1 | Indirect | Indirect cost recovery 7% | lump | 1 | 1 | 1 | 100% |  |  |  | 22000 | 0
TOTAL
Monthly burn rate (actual / months elapsed)
Months of budget remaining at current burn
Forecast over / (under) spend at completion
Note on I26: Positive = forecast overspend, needs ED decision and realignment plan.

## Phasing
Monthly phasing and cash forecast
Plan column per month is entered from the workplan. Actual per month from ledger export. 90-day cash need drives tranche requests 30 days ahead.
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Month | Planned spend | Actual spend | Cumulative plan | Cumulative actual | Variance | Cash received | Cash balance | Next 90-day need | Tranche request due
2026-01 | 20000 | 15200 |  |  |  | 100000
2026-02 | 25000 | 22800 |  |  |  | 0
2026-03 | 40000 | 38900 |  |  |  | 0
2026-04 | 45000 | 44100 |  |  |  | 100000
2026-05 | 45000 | 46700 |  |  |  | 0
2026-06 | 45000 | 43200 |  |  |  | 0
2026-07 | 45000 | 41800 |  |  |  | 100000
2026-08 | 45000 | 44300 |  |  |  | 0
2026-09 | 45000 |  |  |  |  | 0
2026-10 | 40000 |  |  |  |  | 0
2026-11 | 25000 |  |  |  |  | 0
2026-12 | 10400 |  |  |  |  | 0

## Donor rules
Donor rules and ineligible costs for this grant (fill on award day)
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Topic | Rule per agreement | Agreement clause | Note
Budget flexibility between lines | 10% of line without prior approval; above needs written amendment
Reporting frequency | Quarterly financial and narrative, 30 days after quarter end
Ineligible costs | VAT where recoverable, fines, alcohol, gifts, costs outside project period, unapproved international travel
Procurement thresholds | Follow SOC policy or donor's, whichever is stricter
Audit rights and retention | 7 years from final report
Asset disposal | Donor approval before transfer or sale of assets above USD 500
Exchange rate | Rate on date of transaction, source recorded