## Contracts
Operations Registers
One workbook, one owner per sheet. Feeds the dashboard. 'Days to end' uses the As-of date in B5.
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
As of | 2026-09-08
Contract ID | Type (Employment / Consultant / Supplier / Venue / Donor) | Party | Project | Value (USD) | Start | End | Notice days | Renewal count | Signatory | Days to end | Alert | File link
CT-2026-031 | Employment | Example Name A | UNHCR-PPA-2026 | 21600 | 2026-02-01 | 2027-01-31 | 30 | 0 | OD
CT-2026-047 | Employment | Example Name B | UNHCR-PPA-2026 | 4400 | 2026-06-01 | 2026-09-30 | 15 | 3 | OD
CT-2026-052 | Supplier | Cash delivery agent X | UNHCR-PPA-2026 | 2400 | 2026-03-01 | 2026-12-31 | 30 | 0 | ED
CT-2026-060 | Donor | UNICEF PCA | UNICEF-PCA-2026 | 180000 | 2026-04-01 | 2027-03-31 | 60 | 0 | ED

## Procurement
Procurement register
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
PR ID | Date | Project | Description | Est. value (USD) | Route | Quotes received | Supplier | PO number | PO date | GRN date | Invoice paid date | Status | Days open
PR-2026-088 | 2026-08-12 | UNICEF-PCA-2026 | Training kits x35 | 350 |  | 1 | Stationery Co | PO-2026-071 | 2026-08-14 | 2026-08-20 | 2026-08-28 | Closed
PR-2026-091 | 2026-08-25 | UNHCR-PPA-2026 | Vehicle hire Sep-Dec | 3600 |  | 3 | Transport Ltd | PO-2026-074 | 2026-09-01 |  |  | Open

## Travel
Travel and embassy register
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Trip ID | Traveller | Project | Destination | Purpose | Depart | Return | Authorised by | Visa required | Embassy appointment | Visa status | Passport custody receipt | Advance (USD) | Settlement date | Days to settle | Alert
TR-2026-019 | Example Name A | UNHCR-PPA-2026 | Amman | Donor workshop | 2026-09-20 | 2026-09-24 | OD | Y | 2026-09-02 | Issued | PC-014 | 450
TR-2026-015 | Example Name B | UNHCR-PPA-2026 | Sinjar | PDM round 2 | 2026-08-30 | 2026-09-02 | PM | N |  | n/a |  | 120

## Reports due
Donor reporting calendar
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Project | Report | Donor due | Internal due (5 wd before) | Owner | Status | Days to donor due | Alert
UNHCR-PPA-2026 | Q3 narrative and financial | 2026-10-30 | 2026-10-23 | PM / FM | Not started
UNICEF-PCA-2026 | Semi-annual progress | 2026-10-15 | 2026-10-08 | PM | Drafting

## Assets
Asset register (assets above USD 500)
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Asset tag | Description | Project / donor | Purchase date | Cost (USD) | Location | Custodian | Condition | Last verified | Disposal approval
SOC-IQ-0041 | Laptop 14in | UNHCR-PPA-2026 | 2026-02-03 | 820 | Erbil | S-001 | Good | 2026-06-30