## ITT
Indicator Tracking Table (ITT)
One row per indicator. Owner: M&E Officer. Update monthly by the 10th.
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Indicator ID | Project | Logframe level | Indicator definition | Unit | Disaggregation | Baseline | Target | Q1 | Q2 | Q3 | Q4 | Cumulative | % of target | RAG | Data source | Frequency | Responsible | Last verified | Notes
IND-01 | UNHCR-PPA-2026 | Output 1 | Number of IDP households receiving multipurpose cash assistance | households | sex of HoH, governorate | 0 | 1200 | 280 | 310 | [5 empty] | Kobo PDM survey | Quarterly | M&E Officer | 2026-07-10 | Cumulative column: sums quarters for counts, takes latest quarter for % indicators.
IND-02 | UNHCR-PPA-2026 | Outcome 1 | % of assisted households reporting ability to meet basic needs (PDM) | % | sex of HoH | 31 | 70 | 48 | 55 | [5 empty] | Kobo PDM survey | Quarterly | M&E Officer | 2026-07-10 | Cumulative column: sums quarters for counts, takes latest quarter for % indicators.
IND-03 | UNICEF-PCA-2026 | Output 2 | Number of teachers completing psychosocial support training | persons | sex, district | 0 | 150 | 40 | 62 | [5 empty] | Kobo PDM survey | Quarterly | M&E Officer | 2026-07-10 | Cumulative column: sums quarters for counts, takes latest quarter for % indicators.
RAG rule: G at or above 90% of target, A 60-89%, R below 60%. Adjust thresholds per donor in the Notes column.

## Data quality log
Data Quality Log
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Date | Project | Tool / dataset | Issue type | Description | Records affected | Action taken | Owner | Status | Closed date
2026-07-03 | UNHCR-PPA-2026 | PDM round 2 | Duplicate | 12 duplicate household IDs from enumerator E-07 re-uploads | 12 | Duplicates removed, enumerator re-briefed on sync | M&E Officer | Closed | 2026-07-04

## Translation log
Translation Log
Legend: yellow cells with blue text are inputs. Black cells are formulas, do not overwrite. Example rows show expected format, replace them.
Item ID | Project | Source file (Arabic) | Words | Translator | Date sent | Draft received | Reviewer | Review date | Glossary flags | Sensitive content check by | Status | Final file
TR-0041 | UNHCR-PPA-2026 | FGD-W-Mosul-02_AR.docx | 2300 | Contracted translator A | 2026-07-05 | 2026-07-07 | M&E Officer | 2026-07-08 | 2 | PM | Final | FGD-W-Mosul-02_EN_final.docx